## Roles and Responsibilities
Task Title | Lead LAO | Collaborating LAOs | AOs | DMASC | DCP | Comments
Start Up Tasks/Initial Solicitation
Concept/Protocol planning/Develop Project plan | X | X |  | X | X | Communication plan; Timelines - If two or more LAOs collaborate on concept development, the concept will be submitted to DCP for scientific review.
Develop Study manual and distribute | X |  |  |  |  | i. Who is responsible for creating manuals for cross-network studies? Lead LAO ii. How will Lead LAO/DMASC manage manuals to ensure volume control? Same as other studies with numbers and dates. iii. How will amendments to manuals be managed? Same as with other studies and distributed by Lead LAO.
SVAR/eCRFs | X |  |  | X | X | DMASC will build in collaboration with Lead LAO - standard process
Study Initiation Meeting (Prepare and conduct) | X | X |  | X | X | The Lead LAO organizes with participation from collaborating LAOs/AOs, DMASC, DCP.
Regulatory
IND Submission |  |  |  |  | X | DCP's regulatory contractor submits the IND.
Clinicaltrials.gov | X
Regulatory Document collection & review -CCSA/RCR - CVs, statement of investigator, CIRB approval, CIRB approved consent form, financial disclosure, etc., maintain/manage regulatory documentation | X | X
Maintain/manage regulatory documentation (study duration) | X | X |  |  |  | Each LAO manages its AOs.
Creation and Review of IC | X |  |  |  |  | The Lead LAO will develop the IC (part of study startup). Each AO will have specific institution IC and the LAO will review those.
Regulatory Approvals/Tracking | X | X
IRB Submissions | X | X | X |  |  | The Lead LAO submits to the CIRB. Each LAO and AO will submit to their local IRB for acknowledgment.
Monitoring
Develop Monitoring Plan | X | X |  |  |  | SOP 03-03 LAO Oversight Activities - Each LAO monitors its own AOs.
Query Resolution | X | X | X | X
Data Reconciliation | X | X | X | X
Manual Review of Clinical Data/Source Data Verification | X | X |  | X |  | Each LAO is responsible for its own AOs.
Review of Clinical Data | X | X |  | X | X | The Medical Monitor reviews as does the Study Safety Committee and abide by stopping rules.
Review Discrepancy in database |  |  |  | X
Protocol Deviation Reporting and Review | X | X | X | X | X
Site Management
Site Contract and Budget Development/Negotiation | X | X | X |  |  | There is a separate agreement with each collaborating LAO.
Central File Setup/Maintenance (BOX/eTMF) | X |  |  | X |  | There will be study-wide document sharing.
Annual IRB Renewals | X
Biospecimen storage/inventory -CP-CTNet repository | X | X | X | X |  | Receipt, storage and utilization of samples and residual material tracking. It will be study dependent. The site is responsible for inventory/storage of specific specimens.
Biospecimen use for analysis | X | X | X
Biospecimen shipping to site doing analysis | X | X | X |  |  | This will be variable, per the protocol.
Biospecimen shipping to CP-CTNet repository at the trial conclusion | X | X | X |  |  | This will be variable, per the protocol.
Accrual | X | X | X | X |  | All involved parties will ensure that no over enrollment occurs.
Safety
SAE Reporting | I | R | X |  | X | The AO will report to CCSA and DCP with copies to the Lead LAO and Collaborating LAO. I = Informed R = Responsible
Auditing
Audits |  | X | X | X |  | Please see SOP 03-02 Site (LAO/AO) Preparations for Quality Assurance Audits.
Project Management
Lead Study Calls/develop agenda for meetings | X
Recruitment | X | X | X | X |  | The Lead LAO is responsible for trial-wide approvals. Collaborating LAOs/AOs are encouraged to reach out to the Lead LAO for all materials that could be used trial-wide.
Project Team Training | X |  |  | X
Medidata Rave Support |  |  |  | X
Project Status Reports |  |  |  | X
Data Management
SVAR/eCRF development | X |  |  | X | X
Medidata Rave Set up and Validation/Testing |  |  |  | X
Setup for Data Transfers |  |  |  | X
Data Review/Reconciliation by DMs |  |  |  | X
Review discrepancy in database |  |  |  | X
Reconciliation of SAEs |  |  |  |  | X | CCSA will do on behalf of DCP.
Reconciliation of data transfers |  |  |  | X | X | DMASC will do on behalf of DCP when appropriate.
Study Closeout
Prepare for and conduct site close out visits | X | X | X |  |  | Refer to CP-CTNet SOP 04-01 Instructions for Accruing LAO and AO Closeout and CP-CTNet SOP 04-02 Study Closeout. ALL LAOs will need to be responsible for their AOs.
Notification of Closeout Complete | X
Investigational Product Reconciliation | X | X | X |  |  | Consult with MRI Global.
Biospecimen final shipping/reconciliation | X | X | X | X
Medical Monitor
Medical Monitor duties |  |  |  |  | X
Statistical Analysis
Inclusion/Exclusion criteria verification for enrollment | X | X |  | X
DSMB |  |  |  | X | X | Report preparation will be done by the study statistician/DMASC statistician.
Analysis for publications |  |  |  | X |  | The Study Statistician/DMASC Statistician will collaborate on this.
Study Report Writing
Study Manuscript for Publication | X |  |  |  |  | Protocol PI(s) will lead this effort.

## Version and History
2024-01-19 | v1_0 | Original version of document
2025-11-03 | v2_0 | Updated to change DMACC to DMASC